## Slide 1: Hospital Preparedness Exercises Resource Guidebook
Final Briefing Meeting
September 11, 2009
Washington, DC

## Slide 2: Our Team
Principal Investigator: Nathaniel Hupert, MD, MPH
Co-Investigator: Wei Xiong, PhD
Research Project Manager: Melissa Cheung, MPH
Research Assistant: Anh-Thu Vu, MS
Senior Consultant: Doris Varlese, Esq.
Consultant: Nicholas Cagliuso, MPH
Consultant: Jason Barell, MHA

## Slide 3: Overview of Final Briefing
Introduction
Project Methodology/Results
    Initial Kick Off Meeting
    Subject Matter Expert (SME) Meeting
    Document Review Task Force (DRTF) Meetings
    Incorporation of Comments
Project Deliverables (Walk Through)
    Atlas
    Database
    Guidebook/ Pocket Guidebook
Project Final Steps/ Conclusion

## Slide 4: Introduction
 Contract Requirements, Project Purpose, Initial Challenges

## Slide 5: Contract Requirements
General:
    “Comprehensive, cross-talking reference guide to assist community and hospital partners comprehend and meet the panoply of existing recommendations, requirements, and regulations regarding hospital emergency preparedness exercises within the framework of HSEEP guidance.”
Specific:
    Review & update Booz Allen Hamilton environmental scan.
    Developing a draft crosswalk of requirements, recommendations & regulations with existing HSEEP guidance.
    Review of draft document with a large group of stakeholders
    Use-Case with Participating Hospital Planners

## Slide 6: Project Purpose
Tasked by AHRQ & ASPR to:
  Develop a Resource/Reference Tool
    Allow hospitals to work with community partners to meet federal exercise requirements & accreditation standards
    Single point of reference for hospital preparedness planners to comprehend multiple Federal & major non-Federal requirements for exercise creation, conduct, and outcome assessment

## Slide 7: Initial Challenges Related to Contract
Developing a crosswalk of the existing requirements, recommendations, and regulations
  WMC attempted initially (reviewed in SME Meeting)
Defining “exercise evaluation” within HSEEP
  While contract emphasized just “exercise evaluation,” according to HSEEP & other requirements/standards, evaluation is an integrative part of the exercise process
  WMC decided to focus on entire exercise process
Realistic Use-Case/Implementation of WMC materials
  Challenging to work with scheduling of hospital exercises
  WMC attempted initially (later became part of our Document Review Task Force process)

## Slide 8: Project Methodology
Initial Kickoff Meeting, Materials Development, SME Meeting, DRTF Meetings

## Slide 9: Overview: Project Methodology
Task 1: Initial Kickoff Meeting (Oct. 2009)
Task 2-3: Subject Matter Expert Meeting (April 21, 2009)
Task 4: Development of Materials
    Phase I: Nov. 2008 – April 2009
    Phase II: April 2009 – June 2009
    Phase III: Aug. 2009 – Sept. 2009
Task 5-6: Document Review Task Forces (June-Aug. 2009)
Task 7-8: Final Report/Briefing
    Final Briefing: Sept. 11, 2009
    Final Report: Sept. 29, 2009

## Slide 10: Task 1: Initial Kickoff Meeting (Summary)
Guidebook:
  Focus on helping hospitals use HSEEP
Atlas/Database:
  ASPR emphasized wanting a paper version, not electronic database
Other Decisions
  SME Meeting – December/January
October 2008

## Slide 11: Task 4: Development of Materials (Phase I)
Reviewed Booz Allen Hamilton environmental scan
WMC began development of materials
  HSEEP-focused document, 2 products:
    Guidebook
    Atlas
  Worked with 2 consultants, experienced in hospital preparedness
ASPR/AHRQ Conference call (Feb. 2009)
  Sent a current draft to AHRQ & ASPR
    Change in ASPR project personnel
    ASPR did not like HSEEP focus  more emphasis on HPP
    Problematic because the contract is HSEEP focused
    Temporary stop work order placed on project
  Trouble scheduling the SME Meeting (new ASPR personnel, new administration)
Nov. 2008 – Apr. 2009

## Slide 12: Task 2-3: SME Meeting (Summary)
Participants included:
  Federal
    AHRQ, ASPR/HPP, CDC, DHS/FEMA/HSEEP, VHA)
  State Representatives
  Non-Federal
    Accreditation Organizations, AHA, AMA, Red Cross, NFPA
  End Users
    Hospital Preparedness Planners, Trainers

## Slide 13: Task 2-3: SME Meeting Outcomes (Cont’d)
Meeting was a challenging venue to receive feedback from major stakeholders
  Stakeholders all had different perspectives on hospital preparedness
  All wanted their organization to be front & center
Crosswalks: challenging to receive complete approval from all agencies
Many end users commented that the Federal agencies seemed uncoordinated
Participants had trouble differentiating between exercise requirements and overall preparedness

## Slide 14: Task 2-3: SME Meeting (WMC decisions)
Helpful to hear from many stakeholders, yet ASPR/AHRQ and hospital preparedness planners = main clients
Abandoned crosswalks for time being  not enough time to get approval from all organizations
Direction of Materials
    WMC focus on:
    Honoring contract
    Incorporating ASPR comments
    Create useful product for end users

## Slide 15: Task 4: Development of Materials (Phase II)
WMC overhauled documents after SME Meeting
  Created a simplified version of Guidebook
  Revised Atlas listings
Use-Case Implementation
  Initiated contact with potential use-case sites
    Difficulty utilizing State reps provided by ASPR
    WMC: Used own network of hospital preparedness planners
  Trouble with aligning with exercise schedules, H1N1
    Many hospitals did not have the time to participate
    Many also counted H1N1 response to meet exercise req.
    WMC: Use-Case  Document Review Task Force (DRTF)

## Slide 16: Task 5-6: DRTF Meeting (Summary)
Goal: Opportunity for end-users to review documents and provide feedback related to:
  Usability of the Documents & Atlas
  Gaps in the information
  Incorporating their needs to the documents
  Identifying resources & tools to add to atlas
Five Locations:
      Nebraska
      New York
      Georgia
      Washington State (Electronic)
      California (Electronic)

## Slide 17: Task 5-6: DRTF #1, Nebraska (June 2009) Overview
Participants included:
    5 critical access, non-accredited hospitals, with approximately 13-25 beds
    1 State representative
    2 from The Center for Biopreparedness Education of Creighton University
Challenges included:
  Limited resources, both in funding and staffing
  Lack of executive buy-in
  HSEEP is “too big”, “too complicated”

## Slide 18: Task 5-6: DRTF #1, Nebraska (June 2009) Summary of Feedback
Guidebook
    Non-accredited hospitals still look at Joint Commission standards to guide their exercise planning and preparedness activities
    Level of Information: “Just Right”
Atlas
    Participants thought listing information was useful
Database
    Participants thought database was useful
    Concerns about who was going to maintain/host it

## Slide 19: Task 5-6: DRTF #2, New York (July 2009) Overview
Participants included:
    7 accredited hospitals/hospital systems, ranging from 190-850 hospital beds
Challenges included:
  HSEEP usage/compliance “not designed for hospitals”
  Trouble making HSEEP “fit”

## Slide 20: Task 5-6: DRTF #2, New York (July 2009) Summary of Feedback
Guidebook
    Overall: Useful document
    Wanted a checklist/timeline incorporated
    Wanted more emphasis on HVA & After Action Report
Atlas
    Thought listing information was useful
    Wanted a better explanation on how to use the atlas
Database
    Participants highly impressed with electronic database
    Concerns about who was going to maintain/host it

## Slide 21: Task 5-6: DRTF #3, Georgia (July 2009) Overview
Participants included:
    8 accredited hospitals represented (9 participants total)
Challenges included:
  Concerns with meeting Joint Commission accreditation
  Lack of time when it comes to using HSEEP methodology

## Slide 22: Task 5-6: DRTF #3, Georgia (July 2009) Summary of Feedback
Guidebook
    Concerns with documents being out-of-date too quickly
    Comprehension Level of Information: “Just Right”
Atlas
    Liked the way information was presented
Database
    Participants highly impressed with database
    Make it less jargon-heavy

## Slide 23: Task 5-6: DRTF #4, WA State (Aug. 2009) Overview
Participants included:
  3 hospitals represented
  1 State representative
Challenges included:
  Linking the Target Capabilities List to exercises
  HSEEP Compliance
    Too much paperwork
    Do not have time to follow the HSEEP timeline/format

## Slide 24: Task 5-6: DRTF #4, WA State (Aug. 2009) Summary of Feedback
Guidebook
    Overall the guidebook: “great,” compact HSEEP reference guide
    All participants rated guidebook more useful than other HSEEP material
Atlas
    Rated level of information: “Just Right”
Database
    Participants highly impressed with database
    Concerns about who was going to maintain/host it

## Slide 25: Task 5-6: DRTF #5, California (Aug. 2009) Overview
Participants included:
  7 accredited hospitals (6 Joint Commission, 1 AOA)
  1 representative from the CA Hospital Association
  1 State representative
Challenges included:
  Lack of people to conduct exercises
  No time to train staff
  Hospital preparedness planners wear many hats
  HSSEP not hospital friendly, overwhelming, does not fit

## Slide 26: Task 5-6: DRTF #5, California (Aug. 2009) Summary of Feedback
Guidebook
    Found more useful reading guidebook than sitting in an HSEEP course
Atlas
    Almost all participants reported that they could see themselves using the atlas in exercise planning, conduct, or evaluation
Database
    Participants really impressed with database
    Concerns about who was going to maintain/host it

## Slide 27: Task 7-8
Final Briefing (today)
Final Report, in progress

## Slide 28: Project Deliverables (Walkthrough)
 Atlas, Database, Guidebook, Pocket Guidebook

## Slide 29: Role of the Atlas of Resources & Tools
Compendium of the available resources and tools related to planning, conducting, and evaluating hospital preparedness exercises
  Denotes what resources and tools may be useful in meeting certain requirements
  Incorporates HPP & HSEEP resources and tools
Helps hospital preparedness exercise coordinators save time
  Do not have develop new tools, can tailor existing resources & tools to fit needs

## Slide 30: Role of the Database of Resources & Tools
Electronic, searchable version of Atlas
  Normal Search Engine Format
    Modeled after PubMed
  Benefits
    Searchable
    Updatable (Can include the most recent information)
      “Clip” information from relevant web sites
      Hyperlinks
    Web-accessible (potentially)

## Slide 31: Role of the Guidebook
Supplement the Atlas
Assist hospital preparedness coordinators in:
  Meeting the many requirements for preparedness exercises;
  The basics of exercise process;
  3. Using available resources & tools in the exercise process.

## Slide 32: Role of Pocket Guidebook
Takes important information from the guidebook
  Checklists
  Critical exercise requirements and standards

## Slide 33: Role of the Pocket Guidebook
Highlights the essentials of the Guidebook
Includes checklists and key explanations/definitions related to meeting requirements

## Slide 34: Project Next Steps
 Recommendations, Foreseeable Concerns, Conclusion

## Slide 35: Recommendations
Electronic Database
  Most end users saw the greatest potential for this product, which is not an original contract deliverable
  Advantages of database over paper report/atlas
    “Living Tool”

## Slide 36: Current Concerns
Ensuring that all the materials are “living”
  Accreditation Standards updated yearly
  Changes to CMS
  HPP  NHPP, used FOA FY2009
  Who will update/maintain materials
Database
  Weill Cornell sees great potential in this product
    Applied for a no-cost time extension
    Would seek additional funds for development of this product
  Understand ASPR wants an CD database, however the true need is really for a updatable (web-based) system

## Slide 37: Final Report
Submitting with deliverables on Sept. 29, 2009 (unless extension approved)
Final Report will include:
  Project Methodology
  SME Meeting Report
  Findings from DRTFs
  Recommendations to HHS/ASPR/HPP & DHS/HSEEP on implementation & integration issues and other relevant recommendations

## Slide 38: To Be Added
Sample from Atlas
Sample from Guidebook (our old slides)
Full listing from Atlas front material of who was in which review group